## Sheet1
Semester 1
|  |  |  | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24
| Supervisor | Prof. Christopher Freeman
| Student | Yi Farn Lim
Phase | Task |  | % Completion
Literature Review | Industrial Demand and Limitation |  | 100% | 2021-12-13: Progress Report (14/12/21)
| Review of All Controllers Approaches |  | 100% | bar: 2021-10-04 to 2021-10-11
| ILC Approaches |  | 100% | bar: 2021-10-18
Learning (Technical) | MATLAB Crash Course |  | 100% | bar: 2021-10-04
| Revise Control Theory |  | 100% | bar: 2021-10-11
| Simulink & Simscape Tutorial |  | 100% | bar: 2021-10-18
MATLAB | Controller Performance for Gantry axis |  | 66% | bar: 2021-10-18 to 2021-11-01
| Controller Performance for Grasper |  | 0% | bar: 2021-10-25 to 2021-11-15
Simulink Model | Construct Gantry Model (3 axis) |  | 100% | bar: 2021-10-25 to 2021-11-08
| Controller Applied onto Gantry |  | 33% | bar: 2021-11-15 to 2021-11-22
| Construct Grasper Model |  | 0% | bar: 2021-11-29 to 2021-12-13
| Controller Applied onto Grasper |  | 0% | bar: 2021-12-13
Others | Progress Report |  | 100% | bar: 2021-11-22 to 2021-12-13
| Buffer (To complete unfinished task) |  | NIL | [13 empty] | EXAM WEEK
Legend
Completed
Unfinished
Untouched
Deadline
NOTE | Unfinished/untouched tasks will be attempted to be completed during christmas break/exam week