## Sheet1
Semester 2
|  |  |  | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16
| Supervisor | Prof. Christopher Freeman
| Student | Yi Farn Lim
Phase | Task |  | % Completion
Simulink Model | Adapt Controller to grasp different objects |  | 0% | 2022-05-02: Final report (3/5/2 |  |  | Project Viva (19/5/22 - 20/5/22)
| Adapt Controller to reduce grasping force |  | 0% | bar: 2022-02-07
| Further analysis of controller |  | 0% | bar: 2022-02-14
| Improve model based on experiment findings |  | 0% | bar: 2022-03-14 to 2022-03-21
Physical Gantry | Apply different simple controller |  | 0% | bar: 2022-02-21
| Apply controller to grasp different objects |  | 0% | bar: 2022-02-28
| Apply controller to reduce grasping force |  | 0% | bar: 2022-03-07
| Further controller tuning |  | 0% | bar: 2022-03-14 to 2022-03-21
Report Prep | Review of progress report |  | 0% | bar: 2022-03-28 to 2022-04-11
| Future plan and improvements |  | 0% | bar: 2022-04-04 to 2022-04-11
| Final report writeup |  | 0% | bar: 2022-04-04 to 2022-05-02
Project Viva | Preparation |  | 0% | bar: 2022-05-02
Legend
Completed
Unfinished
Untouched
Deadline