## Sheet1
Semester 2
|  |  |  | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16
| Supervisor | Prof. Christopher Freeman
| Student | Yi Farn Lim
Phase | Task |  | % Completion
|  |  |  | 2022-05-02: Final report (3/5/22) |  |  | Project Viva (19/5/22 - 20/5/22)
MATLAB | Design ILC Controller for Gripper (Position) |  | 100% | bar: 2022-01-31
| Design ILC Controller for Gripper (Force) |  | 100% | bar: 2022-02-07
| Subject ILC Controller to Disturbance Scenarios |  | 100% | bar: 2022-02-21 to 2022-02-28
Simulink Model | Design Impedance Controller for Gripper |  | 100% | bar: 2022-02-14
| Subject Impedance Controller to Disturbance Scenarios |  | 100% | bar: 2022-02-21 to 2022-02-28
Physical Gantry | Apply ILC Controllers for 3 Axes |  | 0% | bar: 2022-03-07
| Apply Impedance Controller to Gripper |  | 0% | bar: 2022-03-14
| Apply ILC Controller to Gripper |  | 0% | bar: 2022-03-14
| Subject Controllers to Disturbance Scnarios |  | 0% | bar: 2022-03-21 to 2022-03-28
Report Prep | Review of Progress Report |  | 100% | bar: 2022-03-14 to 2022-04-04
| Final Report Planning/Writeup |  | 100% | bar: 2022-03-28 to 2022-05-02
Project Viva | Preparation |  | 75% | bar: 2022-05-02
Legend
Completed
Unfinished
No Progress
Deadline